## Overview
Project Name
Overview
Reference Information | Location | Comments | Test Documentation for the Ticket Amature application
Use Cases & Requirements | https://github.com/CDierolf/SDEV450-FinalProj/tree/master/Documentation
Reference Material | https://github.com/CDierolf/SDEV450-FinalProj/tree/master/Documentation
Test Environment information | Windows/OSX
End User Documentation | https://github.com/CDierolf/SDEV450-FinalProj/blob/master/README.md
Test Schedule | Week of 12/8/2019
Change Log | Person | Date | Test Instructions
Created Doc | Cdierolf | 2019-12-08
Test Results Summary (Auto Calculated) | Number | Percent
Total Test Cases Passed | 34 | 100%
Total Test Cases Failed | 0 | 0%
Total Test Cases Remaining | 0 | 0%

## Login
Test Info |  | Test Summary |  |  | Instructions
Test Scenario | Successfully login in | Total Passed | 8 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | OSX | Total Failed | 0 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 57
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
AC-0001 | Application Loads Successfully | Login Window Appears |  | Login window appears | Pass | Cdierolf | 2019-12-08
AC-0002 | Create Account link clicked | Create account dialog apperas |  | Create account dialog apperas | Pass | Cdierolf | 2019-12-08
AC-0003 | Cannot create account with blank username | Popup appears, signup fails | "" | Popup appears, signup fails | Pass | Cdierolf | 2019-12-08
AC-0004 | Cannot create account with blank or non-matching passwords | Popup appears, signup fails | ""/"" password/Password, password/password | Popup appears, signup fails | Pass | Cdierolf | 2019-12-08
AC-0005 | Cannot create account with blank or invalid email format | Popup appears, signup fails | "" super@/super@j/super@j.com | Popup appears, signup fails | Pass | Cdierolf | 2019-12-08
AC-0006 | Able to create account providing al validation passes | Popup appears saying account created | super/password/password/super@j.com | Popup appears saying account created | Pass | Cdierolf | 2019-12-08
AC-0007 | User unable to login with invalid account information | User login failed popup appears | ""/"" super/Password | User login failed popup appears | Pass | Cdierolf | 2019-12-08
AC-0008 | User able to log in with valid account information | TicketAmature dashbaord appears | super/password | TicketAmature dashbaord appears | Pass | Cdierolf | 2019-12-08
AC-0009 |  |  |  |  | Not Started
AC-0010 |  |  |  |  | Not Started
AC-0011 |  |  |  |  | Not Started
AC-0012 |  |  |  |  | Not Started
AC-0013 |  |  |  |  | Not Started
AC-0014 |  |  |  |  | Not Started
AC-0015 |  |  |  |  | Not Started
AC-0016 |  |  |  |  | Not Started
AC-0017 |  |  |  |  | Not Started
AC-0018 |  |  |  |  | Not Started
AC-0019 |  |  |  |  | Not Started
AC-0020 |  |  |  |  | Not Started
AC-0021 |  |  |  |  | Not Started
AC-0022 |  |  |  |  | Not Started
AC-0023 |  |  |  |  | Not Started
AC-0024 |  |  |  |  | Not Started
AC-0025 |  |  |  |  | Not Started
AC-0026 |  |  |  |  | Not Started
AC-0027 |  |  |  |  | Not Started
AC-0028 |  |  |  |  | Not Started
AC-0029 |  |  |  |  | Not Started
AC-0030 |  |  |  |  | Not Started
AC-0031 |  |  |  |  | Not Started
AC-0032 |  |  |  |  | Not Started
AC-0033 |  |  |  |  | Not Started
AC-0034 |  |  |  |  | Not Started
AC-0035 |  |  |  |  | Not Started
AC-0036 |  |  |  |  | Not Started
AC-0037 |  |  |  |  | Not Started
AC-0038 |  |  |  |  | Not Started
AC-0039 |  |  |  |  | Not Started
AC-0040 |  |  |  |  | Not Started
AC-0041 |  |  |  |  | Not Started
AC-0042 |  |  |  |  | Not Started
AC-0043 |  |  |  |  | Not Started
AC-0044 |  |  |  |  | Not Started
AC-0045 |  |  |  |  | Not Started
AC-0046 |  |  |  |  | Not Started
AC-0047 |  |  |  |  | Not Started
AC-0048 |  |  |  |  | Not Started
AC-0049 |  |  |  |  | Not Started
AC-0050 |  |  |  |  | Not Started
AC-0051 |  |  |  |  | Not Started
AC-0052 |  |  |  |  | Not Started
AC-0053 |  |  |  |  | Not Started
AC-0054 |  |  |  |  | Not Started
AC-0055 |  |  |  |  | Not Started
AC-0056 |  |  |  |  | Not Started
AC-0057 |  |  |  |  | Not Started
AC-0058 |  |  |  |  | Not Started
AC-0059 |  |  |  |  | Not Started
AC-0060 |  |  |  |  | Not Started
AC-0061 |  |  |  |  | Not Started
AC-0062 |  |  |  |  | Not Started
AC-0063 |  |  |  |  | Not Started
AC-0064 |  |  |  |  | Not Started
AC-0065 |  |  |  |  | Not Started
AC-0066

## View Dashboard
Test Info |  | Test Summary |  |  | Instructions |  |  | © Eric R. Dayal
Test Scenario | Loading the Dashboard post login and all dashboard functionality functioning correctly | Total Passed | 16 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | OSX | Total Failed | 0 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 49
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
BO-0001 | Local events appear | TicketComponent listing specific event info appears |  | TicketComponent listing specific event info appears | Pass | Cdierolf | 2019-12-08
BO-0002 | For new users, no purchased event appear | No ticketComponents appear in this area |  | No ticketComponents appear in this area | Pass | Cdierolf | 2019-12-08
BO-0003 | For users who have purchased events, purchased ticket event info appear in TicketComponents | Ticket components with purchased event information appear |  | Ticket components with purchased event information appear | Pass | Cdierolf | 2019-12-08
BO-0004 | Clicking "My Account"; brings up the user account dialog | User account dialog appears |  | User account dialog appears | Pass | Cdierolf | 2019-12-08
BO-0005 | User able to change all user account information | User able to change all user account information |  | User able to change all user account information | Pass | Cdierolf | 2019-12-08
BO-0006 | User able to change password and login with new password | Successful login with new information and dashbaord appearance |  | Successful login with new information and dashbaord appearance | Pass | Cdierolf | 2019-12-08
BO-0007 | Clicking "Cancel" closes the user account information dialog | User account information dialog closes |  | User account information dialog closes | Pass | Cdierolf | 2019-12-08
BO-0008 | Clicking Logout closes the dashboard and shows the Login window | Dashboard closes and login window appears |  | Dashboard closes and login window appears | Pass | Cdierolf | 2019-12-08
BO-0009 | Clicking "Find Events" changes the view to the FindEventsView | FindEventsView apperas |  | FindEventsView apperas | Pass | Cdierolf | 2019-12-08
BO-0010 | Clicking "Home" takes the user back to the LandingView | LandingView appears |  | LandingView appears | Pass | Cdierolf | 2019-12-08
BO-0011 | Clicking "View Purchased Events" takes the user to the PurchasedEventsView" | PurchasedEventsView appears |  | PurchasedEventsView appears | Pass | Cdierolf | 2019-12-08
BO-0012 | Clicking "Home" takes the user back to the LandingView | LandingView appears |  | LandingView appears | Pass | Cdierolf | 2019-12-08
BO-0013 | Clicking "View Tickets" on a purchased event ticket component shows the event's details in the EventDetailsView | EventDetailsView appears |  | EventDetailsView appears | Pass | Cdierofl | 2019-12-08
BO-0014 | Clicking "Resend Tickets" successfully sends email to user's account email with event and purchase information | Email is received |  | Email is received | Pass | Cdierolf | 2019-12-08
BO-0015 | Clicking "Close" closes the View Details dialog | View details dialog is closed |  | View details dialog is closed | Pass | Cdierolf | 2019-12-08
BO-0016 | Clicking "Purchase Tickets" pulls up the PurchasingView with the events particular venue and seating map loaded | PurchasingView appears with correct venue information and seatmap |  | PurchasingView appears with correct venue information and seatmap | Pass | Cdierofl | 2019-12-08
BO-0017 |  |  |  |  | Not Started
BO-0018 |  |  |  |  | Not Started
BO-0019 |  |  |  |  | Not Started
BO-0020 |  |  |  |  | Not Started
BO-0021 |  |  |  |  | Not Started
BO-0022 |  |  |  |  | Not Started
BO-0023 |  |  |  |  | Not Started
BO-0024 |  |  |  |  | Not Started
BO-0025 |  |  |  |  | Not Started
BO-0026 |  |  |  |  | Not Started
BO-0027 |  |  |  |  | Not Started
BO-0028 |  |  |  |  | Not Started
BO-0029 |  |  |  |  | Not Started
BO-0030 |  |  |  |  | Not Started
BO-0031 |  |  |  |  | Not Started
BO-0032 |  |  |  |  | Not Started
BO-0033 |  |  |  |  | Not Started
BO-0034 |  |  |  |  | Not Started
BO-0035 |  |  |  |  | Not Started
BO-0036 |  |  |  |  | Not Started
BO-0037 |  |  |  |  | Not Started
BO-0038 |  |  |  |  | Not Started
BO-0039 |  |  |  |  | Not Started
BO-0040 |  |  |  |  | Not Started
BO-0041 |  |  |  |  | Not Started
BO-0042 |  |  |  |  | Not Started
BO-0043 |  |  |  |  | Not Started
BO-0044 |  |  |  |  | Not Started
BO-0045 |  |  |  |  | Not Started
BO-0046 |  |  |  |  | Not Started
BO-0047 |  |  |  |  | Not Started
BO-0048 |  |  |  |  | Not Started
BO-0049 |  |  |  |  | Not Started
BO-0050 |  |  |  |  | Not Started
BO-0051 |  |  |  |  | Not Started
BO-0052 |  |  |  |  | Not Started
BO-0053 |  |  |  |  | Not Started
BO-0054 |  |  |  |  | Not Started
BO-0055 |  |  |  |  | Not Started
BO-0056 |  |  |  |  | Not Started
BO-0057 |  |  |  |  | Not Started
BO-0058 |  |  |  |  | Not Started
BO-0059 |  |  |  |  | Not Started
BO-0060 |  |  |  |  | Not Started
BO-0061 |  |  |  |  | Not Started
BO-0062 |  |  |  |  | Not Started
BO-0063 |  |  |  |  | Not Started
BO-0064 |  |  |  |  | Not Started
BO-0065 |  |  |  |  | Not Started
BO-0066

## Find Events
Test Info |  | Test Summary |  |  | Instructions |  |  | © Eric R. Dayal
Test Scenario | Find Events by category, category/postal code or postal code | Total Passed | 10 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | OSX | Total Failed | 0 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 55
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
CO-0001 | Ability to search for events by category only. | TicketComponents load with available event data from API | Taylor Swift | Multiple components pertaining to Taylor Swift events appear | Pass | Cdierolf | 2019-12-08
CO-0002 | Ability to search for events by category/postalcode | TicketComponents load with available event data from API | Rock/37206 | Multiple components pertaining to rock events appear in the given zipcode | Pass | Cdierolf | 2019-12-08
CO-0003 | Ability to search for events by zipcode only | TicketComponents load with available event data from API | 37206 | Multiple components happening in 37206 appear | Pass | Cdierolf | 2019-12-08
CO-0004 | Clicking "Purchase Tickets" on an event with $TBD listed as a price shows popup asking the user to check again | Popup appears and PurchasingView is no loaded |  | Popup appears and PurchasingView is no loaded | Pass | Cdierofl | 2019-12-08
CO-0005 | Clicking "Purchase Tickets" on an event with valid price loads the PurchasingView with correct venue information and event data and seatmap. | PurchasingView with correct venue information and event data and seatmap loaded. |  | PurchasingView with correct venue information and event data and seatmap loaded. | Pass | Cdierolf | 2019-12-08
CO-0006 | "No Events Found" label appears when no events were found by the API | Label apperas |  | Label appaers | Pass | Cdierolf | 2019-12-08
CO-0007 | Clicking "Home" loads the LandingView | LandingView loaded |  | LandingView loaded | Pass | Cdierolf | 2019-12-08
CO-0008 | Clicking "View Purhcased Events" loads the PurchasedEventsView | PurchasedEventsView loaded |  | PurchasedEventsView loaded | Pass | Cdierofl | 2019-12-08
CO-0009 | Pagination is functional only if the next call to the API returns data. | Pagination functional |  | Pagination functional | Pass | Cdierolf | 2019-12-08
CO-0010 | reverse pagination functional only if current page > 0 | Pagination functional |  | Pagination functional | Pass | Cdierofl | 2019-12-08
CO-0011 |  |  |  |  | Not Started
CO-0012 |  |  |  |  | Not Started
CO-0013 |  |  |  |  | Not Started
CO-0014 |  |  |  |  | Not Started
CO-0015 |  |  |  |  | Not Started
CO-0016 |  |  |  |  | Not Started
CO-0017 |  |  |  |  | Not Started
CO-0018 |  |  |  |  | Not Started
CO-0019 |  |  |  |  | Not Started
CO-0020 |  |  |  |  | Not Started
CO-0021 |  |  |  |  | Not Started
CO-0022 |  |  |  |  | Not Started
CO-0023 |  |  |  |  | Not Started
CO-0024 |  |  |  |  | Not Started
CO-0025 |  |  |  |  | Not Started
CO-0026 |  |  |  |  | Not Started
CO-0027 |  |  |  |  | Not Started
CO-0028 |  |  |  |  | Not Started
CO-0029 |  |  |  |  | Not Started
CO-0030 |  |  |  |  | Not Started
CO-0031 |  |  |  |  | Not Started
CO-0032 |  |  |  |  | Not Started
CO-0033 |  |  |  |  | Not Started
CO-0034 |  |  |  |  | Not Started
CO-0035 |  |  |  |  | Not Started
CO-0036 |  |  |  |  | Not Started
CO-0037 |  |  |  |  | Not Started
CO-0038 |  |  |  |  | Not Started
CO-0039 |  |  |  |  | Not Started
CO-0040 |  |  |  |  | Not Started
CO-0041 |  |  |  |  | Not Started
CO-0042 |  |  |  |  | Not Started
CO-0043 |  |  |  |  | Not Started
CO-0044 |  |  |  |  | Not Started
CO-0045 |  |  |  |  | Not Started
CO-0046 |  |  |  |  | Not Started
CO-0047 |  |  |  |  | Not Started
CO-0048 |  |  |  |  | Not Started
CO-0049 |  |  |  |  | Not Started
CO-0050 |  |  |  |  | Not Started
CO-0051 |  |  |  |  | Not Started
CO-0052 |  |  |  |  | Not Started
CO-0053 |  |  |  |  | Not Started
CO-0054 |  |  |  |  | Not Started
CO-0055 |  |  |  |  | Not Started
CO-0056 |  |  |  |  | Not Started
CO-0057 |  |  |  |  | Not Started
CO-0058 |  |  |  |  | Not Started
CO-0059 |  |  |  |  | Not Started
CO-0060 |  |  |  |  | Not Started
CO-0061 |  |  |  |  | Not Started
CO-0062 |  |  |  |  | Not Started
CO-0063 |  |  |  |  | Not Started
CO-0064 |  |  |  |  | Not Started
CO-0065 |  |  |  |  | Not Started
CO-0066

## Purchasing
Test Info |  | Test Summary |  |  | Instructions |  |  | © Eric R. Dayal
Test Scenario | Purchasing seats for an event and finalizing purchase | Total Passed | 9 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | OSX | Total Failed | 0 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 56
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
CO-0001 | User is able to select seats | Clicked seats turned green indicating the user reserved them. The total price is updated based on the event price X number of seats selected. Seat row/column updated to the left. |  | Clicked seats turned green indicating the user reserved them. The total price is updated based on the event price X number of seats selected. Seat row/column updated to the left. | Pass | Cdierolf | 2019-12-08
CO-0002 | User is able to deselect seats | Seats that were previously reserved return to blue "available" color.The total price is updated based on the event price X number of seats selected. Seat row/column updated to the left. |  | Seats that were previously reserved return to blue "available" color.The total price is updated based on the event price X number of seats selected. Seat row/column updated to the left. | Pass | Cdierolf | 2019-12-08
CO-0003 | User is unable to select previously reserved "red seats" | Red seats maintain their status |  | Red seats maintain their status | Pass | Cdierolf | 2019-12-08
CO-0004 | Total price is accurate based on event price * number of seats selected | Total price accurate |  | Total price accurate | Pass | Cdierofl | 2019-12-08
CO-0005 | Clicking "Go Back" takes the user back to Find Events (or LandingView depending on where they came to the PruchasingView from) | Correct View is loaded after clicking "Go Back" |  | Correct View is loaded after clicking "Go Back" | Pass | Cdierolf | 2019-12-08
CO-0006 | Clicking "Checkout" hides the SeatMap and loads the billing information view | Billing information view appears |  | Billing information view appears | Pass | Cdierolf | 2019-12-08
CO-0007 | All fields are required, correct format for CC and EXP date as well as email are required. | Validation fully functional |  | Validation fully functional | Pass | Cdierolf | 2019-12-08
CO-0008 | Clicking "Purchase Tickets" with successful validation results in email being automatically sent with event details and purchase information to the users email | Email received |  | Email received | Pass | Cdierofl | 2019-12-08
CO-0009 | Clicking "Back to Venue" reloads the seatmap | Seatmap reloaded |  | Seatmap reloaded | Pass | Cdierolf | 2019-12-08
CO-0010 |  |  |  |  | Not Started
CO-0011 |  |  |  |  | Not Started
CO-0012 |  |  |  |  | Not Started
CO-0013 |  |  |  |  | Not Started
CO-0014 |  |  |  |  | Not Started
CO-0015 |  |  |  |  | Not Started
CO-0016 |  |  |  |  | Not Started
CO-0017 |  |  |  |  | Not Started
CO-0018 |  |  |  |  | Not Started
CO-0019 |  |  |  |  | Not Started
CO-0020 |  |  |  |  | Not Started
CO-0021 |  |  |  |  | Not Started
CO-0022 |  |  |  |  | Not Started
CO-0023 |  |  |  |  | Not Started
CO-0024 |  |  |  |  | Not Started
CO-0025 |  |  |  |  | Not Started
CO-0026 |  |  |  |  | Not Started
CO-0027 |  |  |  |  | Not Started
CO-0028 |  |  |  |  | Not Started
CO-0029 |  |  |  |  | Not Started
CO-0030 |  |  |  |  | Not Started
CO-0031 |  |  |  |  | Not Started
CO-0032 |  |  |  |  | Not Started
CO-0033 |  |  |  |  | Not Started
CO-0034 |  |  |  |  | Not Started
CO-0035 |  |  |  |  | Not Started
CO-0036 |  |  |  |  | Not Started
CO-0037 |  |  |  |  | Not Started
CO-0038 |  |  |  |  | Not Started
CO-0039 |  |  |  |  | Not Started
CO-0040 |  |  |  |  | Not Started
CO-0041 |  |  |  |  | Not Started
CO-0042 |  |  |  |  | Not Started
CO-0043 |  |  |  |  | Not Started
CO-0044 |  |  |  |  | Not Started
CO-0045 |  |  |  |  | Not Started
CO-0046 |  |  |  |  | Not Started
CO-0047 |  |  |  |  | Not Started
CO-0048 |  |  |  |  | Not Started
CO-0049 |  |  |  |  | Not Started
CO-0050 |  |  |  |  | Not Started
CO-0051 |  |  |  |  | Not Started
CO-0052 |  |  |  |  | Not Started
CO-0053 |  |  |  |  | Not Started
CO-0054 |  |  |  |  | Not Started
CO-0055 |  |  |  |  | Not Started
CO-0056 |  |  |  |  | Not Started
CO-0057 |  |  |  |  | Not Started
CO-0058 |  |  |  |  | Not Started
CO-0059 |  |  |  |  | Not Started
CO-0060 |  |  |  |  | Not Started
CO-0061 |  |  |  |  | Not Started
CO-0062 |  |  |  |  | Not Started
CO-0063 |  |  |  |  | Not Started
CO-0064 |  |  |  |  | Not Started
CO-0065 |  |  |  |  | Not Started
CO-0066

## View Purchased Events
Test Info |  | Test Summary |  |  | Instructions |  |  | © Eric R. Dayal
Test Scenario | User views their previously purchased tickets | Total Passed | 3 |  | In the "Status" column, use Pass, Fail, or Not Started.
Test Environment | OSX | Total Failed | 0 |  | Totals and color highlighting will update automatically based on the Status column
Test Data Source | [link] | Total Remaining | 62
Test Case ID | Test Case Description | Expected Result | Test Data | Actual Result | Status | Tester | Date/Time | Comments
CO-0001 | All of the users purchased events are successfully loaded | Correct number of purchased events loaded as Ticket Components |  | Correct number of purchased events loaded as Ticket Components | Pass | Cdierolf | 2019-12-08
CO-0002 | Clicking "View Details" shows the PurchasedEventDetails View | PurchasedEventDetailsView loaded with correct event details and data |  | PurchasedEventDetailsView loaded with correct event details and data | Pass | Cdierolf | 2019-12-08
CO-0003 | Clicking "Resend Tickets" resends the even details and purchase data to the account email | Email received |  | Email received | Pass | Cdierolf | 2019-12-08
CO-0004 |  |  |  |  | Not Started
CO-0005 |  |  |  |  | Not Started
CO-0006 |  |  |  |  | Not Started
CO-0007 |  |  |  |  | Not Started
CO-0008 |  |  |  |  | Not Started
CO-0009 |  |  |  |  | Not Started
CO-0010 |  |  |  |  | Not Started
CO-0011 |  |  |  |  | Not Started
CO-0012 |  |  |  |  | Not Started
CO-0013 |  |  |  |  | Not Started
CO-0014 |  |  |  |  | Not Started
CO-0015 |  |  |  |  | Not Started
CO-0016 |  |  |  |  | Not Started
CO-0017 |  |  |  |  | Not Started
CO-0018 |  |  |  |  | Not Started
CO-0019 |  |  |  |  | Not Started
CO-0020 |  |  |  |  | Not Started
CO-0021 |  |  |  |  | Not Started
CO-0022 |  |  |  |  | Not Started
CO-0023 |  |  |  |  | Not Started
CO-0024 |  |  |  |  | Not Started
CO-0025 |  |  |  |  | Not Started
CO-0026 |  |  |  |  | Not Started
CO-0027 |  |  |  |  | Not Started
CO-0028 |  |  |  |  | Not Started
CO-0029 |  |  |  |  | Not Started
CO-0030 |  |  |  |  | Not Started
CO-0031 |  |  |  |  | Not Started
CO-0032 |  |  |  |  | Not Started
CO-0033 |  |  |  |  | Not Started
CO-0034 |  |  |  |  | Not Started
CO-0035 |  |  |  |  | Not Started
CO-0036 |  |  |  |  | Not Started
CO-0037 |  |  |  |  | Not Started
CO-0038 |  |  |  |  | Not Started
CO-0039 |  |  |  |  | Not Started
CO-0040 |  |  |  |  | Not Started
CO-0041 |  |  |  |  | Not Started
CO-0042 |  |  |  |  | Not Started
CO-0043 |  |  |  |  | Not Started
CO-0044 |  |  |  |  | Not Started
CO-0045 |  |  |  |  | Not Started
CO-0046 |  |  |  |  | Not Started
CO-0047 |  |  |  |  | Not Started
CO-0048 |  |  |  |  | Not Started
CO-0049 |  |  |  |  | Not Started
CO-0050 |  |  |  |  | Not Started
CO-0051 |  |  |  |  | Not Started
CO-0052 |  |  |  |  | Not Started
CO-0053 |  |  |  |  | Not Started
CO-0054 |  |  |  |  | Not Started
CO-0055 |  |  |  |  | Not Started
CO-0056 |  |  |  |  | Not Started
CO-0057 |  |  |  |  | Not Started
CO-0058 |  |  |  |  | Not Started
CO-0059 |  |  |  |  | Not Started
CO-0060 |  |  |  |  | Not Started
CO-0061 |  |  |  |  | Not Started
CO-0062 |  |  |  |  | Not Started
CO-0063 |  |  |  |  | Not Started
CO-0064 |  |  |  |  | Not Started
CO-0065 |  |  |  |  | Not Started
CO-0066