## Sheet1
|  |  | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Task list | Assignee | Status | 2019-10-06 | 2019-10-13 | 2019-10-20 | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-13
Repository setup | Christopher | Complete
Database setup | Tom | Complete
Database design/ERD | Tom | Complete
DESIGN PHASE
Task list | All | Complete | bar: 2019-10-06 to 2019-10-13
System Design Doc | All | Complete | bar: 2019-10-13 to 2019-10-20
UI Mockups | Stephen, Chrisopher, Neil | Complete | bar: 2019-10-13 to 2019-10-20
IMPLEMENTATION PHASE
Database interface/class design | Tom, Stephen | Complete | bar: 2019-10-20 to 2019-12-01
UI/Database integration | All | Complete | bar: 2019-11-17 to 2019-12-01
Views
-Create account | Christopher | Complete | bar: 2019-10-27
-Log in | Christopher | Complete | bar: 2019-10-27
-Account profile | Stephen | bar: 2019-11-24
-Change password | Stephen | bar: 2019-12-01
-Search events | Christopher, Neil | Complete | bar: 2019-10-20 to 2019-10-27
-Landing | Stephen | Complete | bar: 2019-11-03 to 2019-11-10
-Ticket | Christopher | Complete | bar: 2019-11-03 to 2019-11-10
-Select seat | Neil | Complete | bar: 2019-11-03 to 2019-11-10
-Seat | Neil | Complete | bar: 2019-11-17
-Purchased events | Neil | Complete | bar: 2019-11-10 to 2019-11-17
Email capability | Neil, Christopher | Complete | bar: 2019-11-17 to 2019-11-24
Testing | All
-Validation | bar: 2019-12-08 to 2019-12-13
-View connections |  | Complete | bar: 2019-12-08 to 2019-12-13
--To/from each view in dashboard |  | Complete | bar: 2019-12-08 to 2019-12-13
-Application states |  | Complete | bar: 2019-12-08 to 2019-12-13
--No purchased/nearby events |  | Complete | bar: 2019-12-08 to 2019-12-13
--Canceling orders |  | Complete | bar: 2019-12-08 to 2019-12-13
Database setup
-Table creation | Tom | Complete | bar: 2019-10-06
-Stored procedures | Tom | Complete | bar: 2019-10-13
-Administration | Tom | Complete | bar: 2019-10-20 to 2019-12-13
Ticketmaster API
-Research | Christopher | Complete | bar: 2019-10-06 to 2019-10-13
-Implementation | Christopher | Complete | bar: 2019-10-13 to 2019-10-20
Debugging and Maintenance | All | bar: 2019-11-10 to 2019-12-13